___________________________________________________________________________

2010/SOM3/SCE/014

Agenda Item: 3.5

ATCWG Medium Term Workplan

Purpose: Consideration

- Submitted by: ATCWG Lead Shepherd

|  | - Third SOM Steering Committee on Economic and Technical Cooperation Meeting - Sendai, Japan 24 September 2010 |
| --- | --- |

MEDIUM TERM WORKPLAN

(2010 – 2015)

Name of the Group: ATCWG

- MEDIUM-TERM GOALS (please provide some explanation/description of the medium term goals that the group will work toward in order to facilitate achievement of APEC-wide strategic objectives )

In the period from 2010-2015, ATCWG will serve as a forum for member economies to enhance the capacity of agriculture and its related industries to contribute to economic growth, food security and social well-being in the region. The Medium-Term goals of ATCWG are as follows:

- Improving agricultural production and distribution through increased innovation, nutritional value, and food safety

- Improving human and institutional resource capacities in agriculture through education and training

- Improving aspects of environmental and natural resource management, infrastructure development related to food security

- Improving agricultural information systems and analysis

- Improving the preparations for natural disasters and cross border threats

Please note that the Work Plan will be updated over time as new initiatives developed and new projects funded.

- WORK PROGRAM

| goals/objectives (please indicate the ecotech priority workstream that they support) |  | Action items/Specific processes/activities |  | Expected Outcomes |  | Timeframe |  | Cooperating party (mo/other apec fora) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. Human Security: Food Security |  | 14th APEC ATCWG Annual Meeting in Beijing on 17-19 June in 2010 |  | - A Recommendation has already submitted to Ministerial Meeting on food security from the ATCWG - Provide inputs for preparation for the Ministerial Meeting on Food Security on areas under the mandate of ATCWG - ATCWG TOR had been revised to better reflect APEC’s priorities - Improve food security in APEC which is one of the key pillars in working towards the APEC Food System |  | 2010 |  |  |
| 2.Human Security: Food Security |  | The APEC Food Security Forum was held in August 18-20 in Chinese Taipei |  | - “Action Plans on APEC Food Security” as an outcome - Improve food security in APEC which is one of the key pillars in working towards the APEC Food System |  | August 2010 - |  |  |
| 3. Human Security: Food Security |  | Workshop on Food Productivity and Food Security in APEC Member Economies |  | - Provide a platform to share expertise and to exchange study achievements on food productivity and food security - Develop a strategic, goal-orientated and multi-year approach and strengthen scientific risk-based approaches and cooperation to ensure the health and safety of populations |  | September, 2010 |  |  |
| 4. Human Security: Food Security |  | Enhancing Food Security through a Regional Approach and Wide Stakeholder Participation to Plant Bio-security |  | Explore and propose appropriate actions, mechanisms and frameworks that can facilitate a shared approach to address identified issues, in support of the Leaders’ Declaration in Lima |  | 2010-2011 |  |  |
| 5. Human Security: Food Security |  | Feasibility Study on Cost-Effective Risk Management Strategies for Food Security |  | - Secure food supply at the economy level - Sustainable food security in the APEC region - Strengthened conditions for APEC’s economic development |  | 2010-2014 |  |  |
| 6. Human Security: Food Security |  | Improve capacity building needs to strengthen the food security. Follow up on recommendations at 14th ATCWG Annual Meeting in Beijing on 17-19 June in 2010 made in the following presentations on food security: - Australia’s presentation on” the role of developed economies in ensuring food security in the APEC region” - Thailand’s presentation on “What are the capacity building needs and challenges for developing economies” - APEC Policy Support Unit’s presentation on “Improving Food Markets in APEC Economies: Can the cost of food be lowered?” which contains 17 recommendations, including recommendations for improving food production, food processing and food safety. Also included recommendations for improving economy-wide influences on food security |  | Improve food security in APEC which is one of the key pillars in working towards the APEC Food System |  | 2010 - 2015 |  |  |
| 7. Human Security: Food Security |  | Hold a roundtable to push forward the responsible agricultural investment (RAI) initiative in the APEC region. |  | The overriding output of the roundtable is to promote RAI aiming to create a “win-win-win” situation for recipient economies, local communities and investors. |  | 2011 - 2012 |  |  |
| 8. Human Security：Food Security |  | Promoting Food Security through Innovative Approaches: A Dialogue on Integrating Invasive Species Management for Biodiversity Conservation and Safeguarding Agricultural Productivity and Trade |  | A report that summarizes the shared experiences of APEC member economies, and the discussion of member economies with expert speakers invited to attend the workshop |  | 2011 |  |  |
| 9. Human Security: Food Security |  | Adoption of Post-Harvest Interventions to Ensure Food Security |  | - Post-harvest handling technologies among APEC economies enhanced - Post-harvest losses reduced - Food distribution in the APEC region facilitated. |  | 2012-2015 |  |  |
| 10. Human Security：Food Security And Food Safety |  | Workshop on Building an Efficient Agricultural Technical Transfer Platform to Enhance APEC Food Security and Food Safety |  | - Gather data of all APEC member economies’ agriculture technology status quo, technology demand and supplies and technology transfer policies - Set up direct linkage between technology supply and demand sides and open up APEC’s agricultural technology transfer channels |  | 2010-2011 |  |  |
| 11. Human Security：Food Security And Food Safety |  | Workshop to discuss and exchange information on factors contributing to food price volatility |  | Identify factors contributing to food price volatility. |  | 2011 |  |  |
| 12. Human Security: Emergency Preparedness |  | Risk Analysis on Cross-Border Spread of Animal Influenza in Trade Areas of Borders and Communication for Information |  | Propose a new way of risk analysis on cross-border spread of animal influenza in the trade areas of border |  | 2010-2011 |  |  |
| 13. Regional Economic Integration |  | Conference on improving agricultural technology transfer and development within APEC region |  | A final report summarizing the discussions and next steps in improving agricultural technology transfer within APEC region is to be formulated. This report will facilitate following up actions which will ultimately result in improving a matured agricultural technology transfer environment |  | 2010-2011 |  |  |
| 14. Regional Economic Integration: Information Networks |  | Cooperate with the existing information sharing platforms to deliver knowledge and best practices on Agriculture |  | Build up an comprehensive agriculture information platform. |  | 2010-2015 |  |  |
| 15. Safe Guarding The Quality Of Life Through Sustainable Growth: Work On Energy Efficiency And Renewable Energy |  | APEC-ATCWG Biofuels Network Annual Symposium and Biotrade/Technical Training Workshop |  | Gather information and advanced model to establish ATCWG Biofuels newwork |  | 2011 |  |  |
| 16. Safe Guarding The Quality Of Life Through Sustainable Growth: Work On Climate Change Mitigation And Adaptation |  | Application of Decision-Support System for the Mitigation of Climate-Impacted Slopeland Hazards |  | - An information platform for slopeland disaster mitigation in the APEC region established - Slopeland hazard preparedness, emergency responses and recovery measures of the APEC member economies enhanced - A cooperation mechanism to mitigate slopeland disasters among the APEC member economies established. |  | 2011-2013 |  |  |
| 17. Safe Guarding The Quality Of Life Through Sustainable Growth: Work On Climate Change Mitigation And Adaptation |  | Technology Development of Food Production System for Mitigation of and Adaptation to Climate Change to Ensure Food Security |  | - Greenhouse gas emission from the agricultural sector in the APEC region reduced; - Crop varieties and animal breeds that cope with climate change developed and disseminated; - Sustainable food production under climate change in the APEC economies enhanced. |  | 2011-2013 |  |  |
| 18. Human Security: Food Security & Safe Guarding The Quality Of Life Through Sustainable Growth: Work On Climate Change Mitigation And Adaptation |  | Impacts of Climate Change on APEC Agriculture Production |  | - Researchers in the region will have good chance to exchange information and view points on the experiences of impacts of climate change on agriculture production - Raise awareness of the central and local governments of the impacts of climate change on agriculture production and its impacts to rural society - Policy makers can have good recommendations for developing their own policy |  | 2010-2011 |  |  |
| 19. Human Security: Food Security & Safe Guarding The Quality Of Life Through Sustainable Growth: Work On Climate Change Mitigation And Adaptation |  | Food Security Improvement through Livelihood Adaptation to Climate Variability and Change |  | Improve food security in APEC which is one of the key pillars in working towards the APEC Food System |  | 2011 |  |  |
| 20. Human Security: Food Security & Safe Guarding The Quality Of Life Through Sustainable Growth: Work On Climate Change Mitigation And Adaptation |  | Investment in agriculture, food security, enhance agriculture’s ability to adjust and mitigate the impact of climate change in APEC region |  | - The final workshop report corporate all presentations and economy’s papers will be published, will also be posted in the website - Raise awareness of the central and local governments of in food production, changing approach in spend budget as well as diversified of modalities in mobilize other recourses in agriculture production especially for food security especially in context of climate change - help the government officials/researchers/ private sectors to recommend the solution for each case such in develop plan, coordinate in diversified donors support for food security, mitigation of climate change in agriculture |  | 2011 |  |  |
| 21. Human Security: Food Security & Safe Guarding The Quality Of Life Through Sustainable Growth: Work On Climate Change Mitigation And Adaptation |  | Development and Application of Irrigation Technologies for Adaptation to Climate Change |  | - Water resources for triple functions of agricultural production, livelihoods and ecological balance vitalized - Water sectors to adapt climate change strengthened - Capacities of irrigation facilities in response to water-related disasters enhanced. |  | 2011-2013 |  |  |
| 22. Human Security: Food Security & Safe Guarding The Quality Of Life Through Sustainable Growth: Work On Climate Change Mitigation And Adaptation |  | Enhanced Utilization of Indigenous Vegetables to Meet the Challenge of Climate Change and Food Security |  | - Capacities for APEC members to develop and utilize indigenous vegetables to mitigate the impact of climate change on vegetable supply improved - Sources of micronutrients and other desirable phytochemicals in the APEC region increased - Employment opportunities, especially for the women, in the rural areas created |  | 2011-2014 |  |  |
| 23. Human Security: Prevention and control of emerging infectious diseases |  | APEC Citrus Greening (Hunglongbing) Forum |  | - Partnership and cooperation in technology transfer and policy options identified to ensure to meet specific current/domestic situation, needs and demands in the performance of health management in rehabilitated citrus orchards for preventing resurgence of greening disease - Recommendations to policy makers and other stakeholders on management measures to be taken to combat the widespread of citrus greening to ensure the productive and sustainable citrus production system - Recommendation on APEC-ATCWG action plan for the effective regulatory control in cross border movement of quarantine important invasive pests - Publish a useful Proceedings or guide book on Rehabilitation and Healthy Management of Citrus Greening-Infected Orchards for distribution |  | 2011 |  |  |